## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kalyani | 2026-09-12 | Document Text Extraction Issue | Sprint1 | Kalyani | Technical | Document parsing process ni check chesi extraction issue fix chesam. | 2026-09-01 | Closed | Extraction verified.
2 | Kalyani | 2026-09-12 | Incorrect Document Chunking | Sprint1 | Kalyani | Technical | Chunking parameters adjust chesi generated chunks test chesam. | 2026-09-01 | Closed | Chunking validated.
3 | Kalyani | 2026-09-12 | Embedding Generation Issue | Sprint1 | Kalyani | Technical | Embedding configuration check chesi implementation correct chesam. | 2026-09-02 | Closed | Embeddings generated successfully.
4 | Kalyani | 2026-09-12 | Irrelevant Semantic Search Results | Sprint1 | Kalyani | Functional | Retrieval logic improve chesi project-related queries tho test chesam. | 2026-09-02 | Closed | Retrieval improved.
5 | Kalyani | 2026-09-12 | Missing Project Context in AI Response | Sprint1 | Kalyani | Functional | Retrieved document context ni AI response generation tho connect chesam. | 2026-09-03 | Closed | Contextual responses verified.
6 | Kalyani | 2026-09-18 | Document Text Extraction Issue | Sprint1 | Kalyani | Technical | Document parsing and text extraction process checked and corrected. | 2026-09-09 | Closed | Extraction verified.
7 | Kalyani | 2026-09-18 | Incorrect Document Chunking | Sprint1 | Kalyani | Technical | Chunking parameters adjusted and generated chunks tested. | 2026-09-09 | Closed | Chunking validated.
8 | Kalyani | 2026-09-18 | Embedding Generation Issue | Sprint1 | Kalyani | Technical | Embedding configuration checked and generation process corrected. | 2026-09-10 | Closed | Embeddings generated successfully.
9 | Kalyani | 2026-09-18 | Irrelevant Semantic Search Results | Sprint1 | Kalyani | Functional | Retrieval logic improved and project-related queries tested. | 2026-09-10 | Closed | Retrieval improved.
10 | Kalyani | 2026-09-18 | Missing Project Context in AI Response | Sprint1 | Kalyani | Functional | Retrieved document context connected with AI response generation. | 2026-09-10 | Closed | Contextual responses verified.
11 | Kalyani | 2026-09-18 | Duplicate Risk Analysis Heading | Sprint2 | Kalyani | UI / Functional | Removed the additional manually displayed Risk Analysis heading | 2026-09-10 | Closed | Only one risk analysis heading is displayed.
12 | Kalyani | 2026-09-18 | Duplicate Blocker Analysis Heading | Sprint2 | Kalyani | UI / Functional | Removed the extra “Blockers & Recommended Actions” heading from the Blocker module. | 2026-09-11 | Closed | Duplicate heading issue resolved.
13 | Kalyani | 2026-09-18 | Duplicate Project Intelligence Results | Sprint2 | Kalyani | Functional | Removed repeated Scope, Risk, and Blocker output from the Project Intelligence section. | 2026-09-11 | Closed | Analysis results are displayed only in their respective modules.
14 | Kalyani | 2026-09-18 | Project Insights Dashboard Not Available | Sprint2 | Kalyani | Functional | Added Project Insights and Risk Summary Dashboard section. | 2026-09-12 | Closed | Dashboard section added.
15 | Kalyani | 2026-09-18 | Missing Risk Summary Visualization | Sprint2 | Kalyani | Functional | Added risk priority summary chart for High, Medium, and Low risks. | 2026-09-12 | Closed | Risk summary visualization added.
16 | Kalyani | 2026-09-18 | Missing Blocker Summary Visualization | Sprint2 | Kalyani | Functional | Added blocker priority summary chart. | 2026-09-12 | Closed | Blocker summary visualization added.
17 | Kalyani | 2026-09-18 | Missing Project KPI Cards | Sprint2 | Kalyani | UI / Functional | Added KPI cards for risks and blockers in the dashboard. | 2026-09-13 | Closed | Dashboard KPI cards displayed.
18 | Kalyani | 2026-09-18 | Dashboard Empty State Missing | Sprint2 | Kalyani | Functional | Added a message when analysis is not available. | 2026-09-14 | Closed | User is asked to run analysis first.
19 | Kalyani | 2026-09-18 | Project Health Result Not Shown in Dashboard | Sprint2 | Kalyani | Functional | Connected Project Health analysis with the dashboard. | 2026-09-14 | Closed | Project health information displayed.
20 | Kalyani | 2026-09-18 | Inaccurate Risk and Blocker Counts | Sprint2 | Kalyani | Functional | Risk and blocker count logic reviewed and improved. | 2026-09-15 | Open | Exact structured AI-based counting is still required.
21 | Kalyani | 2026-09-18 | Delivery Forecasting Not Fully Implemented | Sprint2 | Kalyani | Functional | Delivery forecasting requirement reviewed for future implementation. | 2026-09-16 | Open | Delivery forecast needs a separate implementation.
22 | Kalyani | 2026-09-26 | Risk Recommendations Not Available | Sprint2 | Kalyani | Functional | Risk analysis recommendations reviewed and actionable guidance added. | 2026-09-19 | Closed | Risk recommendations verified.
23 | Kalyani | 2026-09-28 | Blocker Recommended Actions Missing | Sprint2 | Kalyani | Functional | Blocker analysis recommendations reviewed and recommended actions added. | 2026-09-19 | Closed | Blocker actions verified.
24 | Kalyani | 2026-10-01 | Project Report Download Issue | Sprint2 | Kalyani | Functional | Project report download functionality reviewed and verified. | 2026-09-20 | Closed | Report download verified.
25 | Kalyani | 2026-10-01 | Health Dimension Details Missing | Sprint2 | Kalyani | Functional | Project health dimension scores reviewed and displayed. | 2026-09-20 | Closed | Health dimensions verified.
26 | Kalyani | 2026-10-01 | Consolidated Project Overview Missing | Sprint2 | Kalyani | Functional | Consolidated project overview reviewed and integrated. | 2026-09-21 | Closed | Project overview verified.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others